## Sheet1
Module | Resource | Days | Start Date | EndDate
Front Office | Mahinda | 5 | 25/12/2014 | 30/12/2014
Trial Calculation
Pledge Loan
Revolving Loan
Invoice Discounting
Variable Interest
Application Maintenance | Sham | 5 | 23/12/2014 | 28/12/2014
Open an Application
Security Details
Amendment Report | Pending
Document Check List | Pending
Submit for Approvals
Application Status Inquiry
Cancel Application
Approvals
First Level Approval
Second Level Approvals
Contract Maintenance | Mahinda | 2 | 28/12/2014 | 30/12/2014
Initiate Contract
Activation
Legal Documents
Offer Letter
Acceptance Receipts
Agreement
Letter of Demand
Reminder Print
Customer Statement
Information Consol
Contract Information
Rental Schedule
Security Details
Contract Closure | Mahinda | 5 | 31/12/2014 | 2015-05-01
Normal Closure
Early Settlement
Reschedulement
Contract Termination
Legal Transfer
Reports
Arrases Reports
Due Rental Report
Security Information Report
Portfolio Report
Income Reports
System Day End | Shaja | 5 | 25/12/2014 | 30/12/2014
Overpayment Process
ODI Calculation
Rentals Maturity Process
Post-Dated Cheque Process
Arrears Process
Laps Contracts
Reminder Process
Settlement | Shaja | 3 | 31/12/2014 | 2015-03-01
Receipts
Receipt Cancellation
Cheque Return
Client Security | Sham | 5 | 28/12/2014 | 2014-03-01
Security Utilization
Security Approval
Replace Security
Release Security