## Slide 1
Project Implementation
Progress
ModularFour Finsoft Solution
MODULARFOUR SOLUTION PVT LTD

## Slide 2
Contents.
MODULARFOUR SOLUTION PVT LTD
Project Overview
Past Data
Current Situation
Objectives and Goals
Questions

## Slide 3
Project Overview.
MODULARFOUR SOLUTION PVT LTD
Task | Planned Date | Actual Date
Project Start | 28-Jan-2012 | 28-Jan-2012
System Implementation | 01-Apr-2012 | 15-Sep-2012
Data Entering | 01-May-2012 | 20-Sep-2012
Pararell run | 1 Month | Not Yet Started
Live Run | 01-Aug-2012 | Not yet Decided

## Slide 4
Real Estate.
MODULARFOUR SOLUTION PVT LTD
Past Data.
Chart: 
| Projects | Budgets | Reservation | Billing | Sold Note | Receipts
 | 1 | 1 | 1 | 0 | 0.2 | 1
Loan.
Chart: 
| Loan | TC | Applications | Contracts | Receipts
 | 1 | 0.1 | 0.1 | 0.1 | 0.1
Chart: 
| GL | Account Balances | Ledger Entries | Vouchers | Petty Cash | Bank Rec
 | 1 | 0 | 0.2 | 0 | 0 | 0
General Ledger.

## Slide 5
MODULARFOUR SOLUTION PVT LTD
Current Situation.
Back log Data Entering
Total No of Receipt 1500
Entered Receipts for 7 Days 74
5%
Per Day 11
Expected Period to Finish 136 d / 6 M

## Slide 6
MODULARFOUR SOLUTION PVT LTD
Objectives and Goals.
Finish Data Entering ASAP by EOM
Start Live Run by 01-02-2013
Increase Data Entry Resources

## Slide 7
MODULARFOUR SOLUTION PVT LTD

## Slide 8
MODULARFOUR SOLUTION PVT LTD