## Sheet1
LHP Modifications and Errors
| Description | Who | Priority | Modification/Error | Status (DASS) | Comments (LHP)
1 | BOC - Cheque view is slow | Roshan | 1 | Error | Done | OK
2 | Cannot do “Order confirmation” & “Order verification” while print preview is generating | Roshan | 2 | Error | Done | OK
3 | Print preview generating is slow | Roshan | 3 | Error | Done | OK
4 | In the order form printing when the number of pages is high, error is occurring as “background processing” and gets closed. | Roshan | 4 | Error | Done | OK
5 | COM - Having slowness in the job detail report | Roshan | 5 | Error | Done | OK
6 | HNB - Reply mail is not sending to the bank.*** should be available in Reply mail option | Mahinda | 1 | Error | Done
7 | HNB - Cannot create mini branches. Error: “Unknown error occurred” | Mahinda | 2 | Error | Done | OK
8 | HNB - Cannot create new cross type. Error:”Value cannot be null. Parameter:TYPE” | Mahinda | 3 | Error | Done | Pending
9 | COM - Reply mail is not generating when the order file size is large | Mahinda | 4 | Error
10 | Add “user”, “date”, “time”,”company”,”product” to the order details of the file uploading method | Mahinda | 5 | Modification | Done
11 | In the morning Tomcat sever getting hang up | Mahinda | 6 | Modification | Done
12 | Cannot set the day end of the file uploading system (Java) without canalling the orders. | Mahinda | 7 | Error | Done
13 | Audit trail system is not working in both ‘Java’ & ‘SQL’ system | Mahinda | 8 | Error | Done | Pending
14 | Method of disabling a system user account | Mahinda | 9 | Modification | Done
15 | BOC - Cannot get archive data |  |  | Modification
16 | COM - Cannot get archive data |  |  | Modification
17 | BOC - Delivery acknowledgment view is slow | Roshan | 6 | Error | Done | OK
18 | COM - Add TC number to the job detail report | Mahinda | 7 | Modification | Done
19 | Seylan - At the first time of the downloading excel file error occurring “NOT FOUND” | Mahinda | 10 | Error
20 | Union - Add TC number to the job detail report | Roshan | 8 | Modification
21 | Multiple order correction print (For the COM bank this is ok) HNB & Ammana Error occurred | Roshan | 9 | Error
22 | Page size need to be set as “custom “ in the ‘cheque printing’, ‘Correction Printing’ & ‘order form’
23 | In the CRN reports, current date (server date) appear as the report date. Report date should be the actual processed date. Order Date Should be Introduced
24 | If the Account number has not given from the bank, cheque should be print without the Account number. (counter leafs )
25 | In the job detail report “MICR” and “Customer Account No” columns need to change. (Currently Customer Account no display in the MICR column. And MICR no display in the Customer Account No column. )
26
27
28